## Read Me First
How to use this tracker
This plan runs 100 days: 19 Sep 2026 -> 27 Dec 2026 (matches your Sep-Dec 2026 semester).
Structure:
- Weekdays are kept light (1-1.5h) since your JKUAT timetable already fills your days.
- Weekends carry the heavier 'deep work' blocks (2.5-3h each) - this is where most real progress happens.
- The 'Class Schedule' column repeats your fixed university timetable so you always see it alongside your self-study plan.
- The 'Your Free Window' column is a suggestion, not a rule - if an unlisted extra class or CAT lands there, swap it for another open slot the same day, or push it to the weekend buffer.
If a day gets missed:
- Mark it 'Skipped' rather than deleting it - the Dashboard tracks Skipped days separately so you always see your true completion rate.
- Week 14 (Days 94-100) is a built-in buffer/catch-up week - use it to absorb missed days before the 100 days end.
Your target: getting even 2/3 of these 100 days marked 'Done' (about 67 days) puts you meaningfully ahead of where you are today by January/February - the Dashboard sheet calculates this target automatically.
Daily habit: update the Status column (dropdown) each evening - it takes 10 seconds and keeps the Dashboard accurate.

## 100-Day Tracker
Day | Date | Weekday | Phase | Week / Theme | Class Schedule (fixed) | Your Free Window | Today's Task | Resource / Platform | Est. Time (h) | Status | Notes
1 | 2026-09-19 | Saturday | Phase 1: Foundations | Orientation | No scheduled classes | Deep-work block (~3h) | Kick-off: read your full learning roadmap; set your 100-day goal; set up a dedicated folder/notebook for tracking | - | 3 | Not Started
2 | 2026-09-20 | Sunday | Phase 1: Foundations | Orientation | No scheduled classes | Deep-work + weekly review (~2.5h) | Create GitHub account + repo '100-day-ai-journey'; install Python 3 and VS Code | github.com | 2.5 | Not Started
3 | 2026-09-21 | Monday | Phase 1: Foundations | Week 1: Setup & Refresh | 08:00-10:00 SMA2321 Numerical Analysis I (CLB106) | Evening 18:00-19:30 (~1.5h) | Refresh linear algebra: vectors, matrices, eigenvalues (eps 1-3) | 3Blue1Brown - Essence of Linear Algebra | 1.5 | Not Started
4 | 2026-09-22 | Tuesday | Phase 1: Foundations | Week 1: Setup & Refresh | 08:00-10:00 STA2300 Theory of Estimation (CLB103); 10:00-12:00 SMA2301 Real Analysis I (CTC201) | Evening 18:00-20:00 (~2h) | Python refresher: functions, NumPy basics, virtual environments | NumPy Quickstart / official Python docs | 2 | Not Started
5 | 2026-09-23 | Wednesday | Phase 1: Foundations | Week 1: Setup & Refresh | 10:00-12:00 SMA2303 Group Theory I (CTC202); 16:00-18:00 SMA2322 Fluid Mechanics I (CTC04) | Morning 08:00-09:30 + Evening 18:30-20:00 (~3h) | Probability refresher: distributions, expectation, variance | MIT OCW 18.05 lecture notes | 1.5 | Not Started
6 | 2026-09-24 | Thursday | Phase 1: Foundations | Week 1: Setup & Refresh | 14:00-15:00 SMA2306 Linear Algebra II (CTC204); 16:00-17:00 SMA2304 ODE I (NSC Lobby) | Morning (free) + Evening 17:30-19:00 (~2h) | Install PyTorch; work through the 60-minute Blitz tutorial | pytorch.org/tutorials | 1.5 | Not Started
7 | 2026-09-25 | Friday | Phase 1: Foundations | Week 1: Setup & Refresh | 09:00-11:00 ICS2311 Computer Graphics (PAM LAB A); 11:00-13:00 SMA2308 Intro. Computational Maths (PAM LAB B) | Afternoon 13:30-15:00 (~1.5h) | Create GitHub account + repo '100-day-ai-journey'; write a README with your goal | github.com | 1 | Not Started
8 | 2026-09-26 | Saturday | Phase 1: Foundations | Week 1: Setup & Refresh | No scheduled classes | Deep-work block (~3h) | Deep work: finish PyTorch Blitz tutorial, push first notebook to GitHub | pytorch.org/tutorials | 3 | Not Started
9 | 2026-09-27 | Sunday | Phase 1: Foundations | Week 1: Setup & Refresh | No scheduled classes | Deep-work + weekly review (~2.5h) | Weekly review: log what you learned; sign up for BlueDot AI Safety Fundamentals | bluedot.org / aisafetyfundamentals.com | 2.5 | Not Started
10 | 2026-09-28 | Monday | Phase 1: Foundations | Week 2: PyTorch Fundamentals + fast.ai Start | 08:00-10:00 SMA2321 Numerical Analysis I (CLB106) | Evening 18:00-19:30 (~1.5h) | fast.ai Lesson 1: watch + take notes (image classification intro) | course.fast.ai | 1.5 | Not Started
11 | 2026-09-29 | Tuesday | Phase 1: Foundations | Week 2: PyTorch Fundamentals + fast.ai Start | 08:00-10:00 STA2300 Theory of Estimation (CLB103); 10:00-12:00 SMA2301 Real Analysis I (CTC201) | Evening 18:00-20:00 (~2h) | fast.ai Lesson 1: hands-on notebook (Colab/Kaggle) | course.fast.ai | 2 | Not Started
12 | 2026-09-30 | Wednesday | Phase 1: Foundations | Week 2: PyTorch Fundamentals + fast.ai Start | 10:00-12:00 SMA2303 Group Theory I (CTC202); 16:00-18:00 SMA2322 Fluid Mechanics I (CTC04) | Morning 08:00-09:30 + Evening 18:30-20:00 (~3h) | BlueDot AISF Week 1: 'Transformative AI and Current Trajectory' | aisafetyfundamentals.com | 1.5 | Not Started
13 | 2026-10-01 | Thursday | Phase 1: Foundations | Week 2: PyTorch Fundamentals + fast.ai Start | 14:00-15:00 SMA2306 Linear Algebra II (CTC204); 16:00-17:00 SMA2304 ODE I (NSC Lobby) | Morning (free) + Evening 17:30-19:00 (~2h) | PyTorch tensors & autograd: practice exercises | pytorch.org/tutorials | 1.5 | Not Started
14 | 2026-10-02 | Friday | Phase 1: Foundations | Week 2: PyTorch Fundamentals + fast.ai Start | 09:00-11:00 ICS2311 Computer Graphics (PAM LAB A); 11:00-13:00 SMA2308 Intro. Computational Maths (PAM LAB B) | Afternoon 13:30-15:00 (~1.5h) | Review week's PyTorch code; tidy up GitHub repo + commit notes | - | 1 | Not Started
15 | 2026-10-03 | Saturday | Phase 1: Foundations | Week 2: PyTorch Fundamentals + fast.ai Start | No scheduled classes | Deep-work block (~3h) | Deep work: fast.ai Lesson 2 + hands-on project | course.fast.ai | 3 | Not Started
16 | 2026-10-04 | Sunday | Phase 1: Foundations | Week 2: PyTorch Fundamentals + fast.ai Start | No scheduled classes | Deep-work + weekly review (~2.5h) | Weekly review; install Lean 4 + VS Code extension for next week | leanprover.github.io | 2.5 | Not Started
17 | 2026-10-05 | Monday | Phase 2: Deep Learning & Alignment Core | Week 3: Neural Net Fundamentals + Outer Alignment | 08:00-10:00 SMA2321 Numerical Analysis I (CLB106) | Evening 18:00-19:30 (~1.5h) | fast.ai Lesson 3: watch + notes | course.fast.ai | 1.5 | Not Started
18 | 2026-10-06 | Tuesday | Phase 2: Deep Learning & Alignment Core | Week 3: Neural Net Fundamentals + Outer Alignment | 08:00-10:00 STA2300 Theory of Estimation (CLB103); 10:00-12:00 SMA2301 Real Analysis I (CTC201) | Evening 18:00-20:00 (~2h) | fast.ai Lesson 3: hands-on notebook exercise | course.fast.ai | 2 | Not Started
19 | 2026-10-07 | Wednesday | Phase 2: Deep Learning & Alignment Core | Week 3: Neural Net Fundamentals + Outer Alignment | 10:00-12:00 SMA2303 Group Theory I (CTC202); 16:00-18:00 SMA2322 Fluid Mechanics I (CTC04) | Morning 08:00-09:30 + Evening 18:30-20:00 (~3h) | BlueDot AISF Week 2: 'Outer Alignment' (reward misspecification, RLHF) | aisafetyfundamentals.com | 1.5 | Not Started
20 | 2026-10-08 | Thursday | Phase 2: Deep Learning & Alignment Core | Week 3: Neural Net Fundamentals + Outer Alignment | 14:00-15:00 SMA2306 Linear Algebra II (CTC204); 16:00-17:00 SMA2304 ODE I (NSC Lobby) | Morning (free) + Evening 17:30-19:00 (~2h) | Lean 4 Ch.1-2: types, terms, basic tactics | Theorem Proving in Lean 4 | 1.5 | Not Started
21 | 2026-10-09 | Friday | Phase 2: Deep Learning & Alignment Core | Week 3: Neural Net Fundamentals + Outer Alignment | 09:00-11:00 ICS2311 Computer Graphics (PAM LAB A); 11:00-13:00 SMA2308 Intro. Computational Maths (PAM LAB B) | Afternoon 13:30-15:00 (~1.5h) | Consolidate notes on outer alignment; summarize in your own words | - | 1 | Not Started
22 | 2026-10-10 | Saturday | Phase 2: Deep Learning & Alignment Core | Week 3: Neural Net Fundamentals + Outer Alignment | No scheduled classes | Deep-work block (~3h) | Deep work: fast.ai Lesson 4 | course.fast.ai | 3 | Not Started
23 | 2026-10-11 | Sunday | Phase 2: Deep Learning & Alignment Core | Week 3: Neural Net Fundamentals + Outer Alignment | No scheduled classes | Deep-work + weekly review (~2.5h) | Weekly review + plan week 4 | - | 2.5 | Not Started
24 | 2026-10-12 | Monday | Phase 2: Deep Learning & Alignment Core | Week 4: Transformers Intro + Inner Alignment | 08:00-10:00 SMA2321 Numerical Analysis I (CLB106) | Evening 18:00-19:30 (~1.5h) | Read 'The Illustrated Transformer' (Jay Alammar) | jalammar.github.io | 1.5 | Not Started
25 | 2026-10-13 | Tuesday | Phase 2: Deep Learning & Alignment Core | Week 4: Transformers Intro + Inner Alignment | 08:00-10:00 STA2300 Theory of Estimation (CLB103); 10:00-12:00 SMA2301 Real Analysis I (CTC201) | Evening 18:00-20:00 (~2h) | HuggingFace Transformers quick-start: load and run a small model | huggingface.co/docs | 2 | Not Started
26 | 2026-10-14 | Wednesday | Phase 2: Deep Learning & Alignment Core | Week 4: Transformers Intro + Inner Alignment | 10:00-12:00 SMA2303 Group Theory I (CTC202); 16:00-18:00 SMA2322 Fluid Mechanics I (CTC04) | Morning 08:00-09:30 + Evening 18:30-20:00 (~3h) | BlueDot AISF Week 3: 'Inner Alignment' (deception, goal misgeneralization) | aisafetyfundamentals.com | 1.5 | Not Started
27 | 2026-10-15 | Thursday | Phase 2: Deep Learning & Alignment Core | Week 4: Transformers Intro + Inner Alignment | 14:00-15:00 SMA2306 Linear Algebra II (CTC204); 16:00-17:00 SMA2304 ODE I (NSC Lobby) | Morning (free) + Evening 17:30-19:00 (~2h) | Lean 4 Ch.3-4: operators, quantifiers, structured proofs | Theorem Proving in Lean 4 | 1.5 | Not Started
28 | 2026-10-16 | Friday | Phase 2: Deep Learning & Alignment Core | Week 4: Transformers Intro + Inner Alignment | 09:00-11:00 ICS2311 Computer Graphics (PAM LAB A); 11:00-13:00 SMA2308 Intro. Computational Maths (PAM LAB B) | Afternoon 13:30-15:00 (~1.5h) | Review + write a 200-word summary of inner vs outer alignment | - | 1 | Not Started
29 | 2026-10-17 | Saturday | Phase 2: Deep Learning & Alignment Core | Week 4: Transformers Intro + Inner Alignment | No scheduled classes | Deep-work block (~3h) | Deep work: HuggingFace hands-on mini-project (fine-tune a tiny model) | huggingface.co | 3 | Not Started
30 | 2026-10-18 | Sunday | Phase 2: Deep Learning & Alignment Core | Week 4: Transformers Intro + Inner Alignment | No scheduled classes | Deep-work + weekly review (~2.5h) | Weekly review + plan week 5 | - | 2.5 | Not Started
31 | 2026-10-19 | Monday | Phase 2: Deep Learning & Alignment Core | Week 5: Mechanistic Interpretability Intro + Threat Models | 08:00-10:00 SMA2321 Numerical Analysis I (CLB106) | Evening 18:00-19:30 (~1.5h) | Watch Neel Nanda's intro to mechanistic interpretability | neelnanda.io | 1.5 | Not Started
32 | 2026-10-20 | Tuesday | Phase 2: Deep Learning & Alignment Core | Week 5: Mechanistic Interpretability Intro + Threat Models | 08:00-10:00 STA2300 Theory of Estimation (CLB103); 10:00-12:00 SMA2301 Real Analysis I (CTC201) | Evening 18:00-20:00 (~2h) | TransformerLens tutorial: basic circuit analysis notebook | github.com/TransformerLensOrg/TransformerLens | 2 | Not Started
33 | 2026-10-21 | Wednesday | Phase 2: Deep Learning & Alignment Core | Week 5: Mechanistic Interpretability Intro + Threat Models | 10:00-12:00 SMA2303 Group Theory I (CTC202); 16:00-18:00 SMA2322 Fluid Mechanics I (CTC04) | Morning 08:00-09:30 + Evening 18:30-20:00 (~3h) | BlueDot AISF Week 4: 'Threat Models' | aisafetyfundamentals.com | 1.5 | Not Started
34 | 2026-10-22 | Thursday | Phase 2: Deep Learning & Alignment Core | Week 5: Mechanistic Interpretability Intro + Threat Models | 14:00-15:00 SMA2306 Linear Algebra II (CTC204); 16:00-17:00 SMA2304 ODE I (NSC Lobby) | Morning (free) + Evening 17:30-19:00 (~2h) | Lean 4 Ch.5: induction and inductive types | Theorem Proving in Lean 4 | 1.5 | Not Started
35 | 2026-10-23 | Friday | Phase 2: Deep Learning & Alignment Core | Week 5: Mechanistic Interpretability Intro + Threat Models | 09:00-11:00 ICS2311 Computer Graphics (PAM LAB A); 11:00-13:00 SMA2308 Intro. Computational Maths (PAM LAB B) | Afternoon 13:30-15:00 (~1.5h) | Review; note 3 open questions to explore later | - | 1 | Not Started
36 | 2026-10-24 | Saturday | Phase 2: Deep Learning & Alignment Core | Week 5: Mechanistic Interpretability Intro + Threat Models | No scheduled classes | Deep-work block (~3h) | Deep work: analyze attention patterns of a small model | TransformerLens | 3 | Not Started
37 | 2026-10-25 | Sunday | Phase 2: Deep Learning & Alignment Core | Week 5: Mechanistic Interpretability Intro + Threat Models | No scheduled classes | Deep-work + weekly review (~2.5h) | Weekly review + plan week 6 | - | 2.5 | Not Started
38 | 2026-10-26 | Monday | Phase 2: Deep Learning & Alignment Core | Week 6: Verification Tools Setup + Technical Safety I | 08:00-10:00 SMA2321 Numerical Analysis I (CLB106) | Evening 18:00-19:30 (~1.5h) | Install Marabou; run its example verification query | github.com/NeuralNetworkVerification/Marabou | 1.5 | Not Started
39 | 2026-10-27 | Tuesday | Phase 2: Deep Learning & Alignment Core | Week 6: Verification Tools Setup + Technical Safety I | 08:00-10:00 STA2300 Theory of Estimation (CLB103); 10:00-12:00 SMA2301 Real Analysis I (CTC201) | Evening 18:00-20:00 (~2h) | Install alpha-beta-CROWN; verify robustness of a toy MNIST classifier | github.com/Verified-Intelligence/alpha-beta-CROWN | 2 | Not Started
40 | 2026-10-28 | Wednesday | Phase 2: Deep Learning & Alignment Core | Week 6: Verification Tools Setup + Technical Safety I | 10:00-12:00 SMA2303 Group Theory I (CTC202); 16:00-18:00 SMA2322 Fluid Mechanics I (CTC04) | Morning 08:00-09:30 + Evening 18:30-20:00 (~3h) | BlueDot AISF Week 5: 'Technical Safety Approaches, Part 1' | aisafetyfundamentals.com | 1.5 | Not Started
41 | 2026-10-29 | Thursday | Phase 2: Deep Learning & Alignment Core | Week 6: Verification Tools Setup + Technical Safety I | 14:00-15:00 SMA2306 Linear Algebra II (CTC204); 16:00-17:00 SMA2304 ODE I (NSC Lobby) | Morning (free) + Evening 17:30-19:00 (~2h) | Start Mathematics in Lean: intro chapter | leanprover-community.github.io/mathematics_in_lein | 1.5 | Not Started
42 | 2026-10-30 | Friday | Phase 2: Deep Learning & Alignment Core | Week 6: Verification Tools Setup + Technical Safety I | 09:00-11:00 ICS2311 Computer Graphics (PAM LAB A); 11:00-13:00 SMA2308 Intro. Computational Maths (PAM LAB B) | Afternoon 13:30-15:00 (~1.5h) | Review; document Marabou/CROWN setup steps in your repo | - | 1 | Not Started
43 | 2026-10-31 | Saturday | Phase 2: Deep Learning & Alignment Core | Week 6: Verification Tools Setup + Technical Safety I | No scheduled classes | Deep-work block (~3h) | Deep work: combine a small PyTorch model with a verification tool end-to-end | - | 3 | Not Started
44 | 2026-11-01 | Sunday | Phase 2: Deep Learning & Alignment Core | Week 6: Verification Tools Setup + Technical Safety I | No scheduled classes | Deep-work + weekly review (~2.5h) | Weekly review; decide which specialization gets more weight (Path 1 vs Path 2) | - | 2.5 | Not Started
45 | 2026-11-02 | Monday | Phase 3: Specialization Practice | Week 7: Specialization Exercises I | 08:00-10:00 SMA2321 Numerical Analysis I (CLB106) | Evening 18:00-19:30 (~1.5h) | Start ARENA-style exercises (mech-interp / RL fundamentals, public materials) | bluedot.org/courses/arena | 1.5 | Not Started
46 | 2026-11-03 | Tuesday | Phase 3: Specialization Practice | Week 7: Specialization Exercises I | 08:00-10:00 STA2300 Theory of Estimation (CLB103); 10:00-12:00 SMA2301 Real Analysis I (CTC201) | Evening 18:00-20:00 (~2h) | Continue ARENA-style exercises | bluedot.org/courses/arena | 2 | Not Started
47 | 2026-11-04 | Wednesday | Phase 3: Specialization Practice | Week 7: Specialization Exercises I | 10:00-12:00 SMA2303 Group Theory I (CTC202); 16:00-18:00 SMA2322 Fluid Mechanics I (CTC04) | Morning 08:00-09:30 + Evening 18:30-20:00 (~3h) | BlueDot AISF Week 6: 'Technical Safety Approaches, Part 2' | aisafetyfundamentals.com | 1.5 | Not Started
48 | 2026-11-05 | Thursday | Phase 3: Specialization Practice | Week 7: Specialization Exercises I | 14:00-15:00 SMA2306 Linear Algebra II (CTC204); 16:00-17:00 SMA2304 ODE I (NSC Lobby) | Morning (free) + Evening 17:30-19:00 (~2h) | Lean: formalize and prove one small numeric/algebraic fact end-to-end | Mathematics in Lean | 1.5 | Not Started
49 | 2026-11-06 | Friday | Phase 3: Specialization Practice | Week 7: Specialization Exercises I | 09:00-11:00 ICS2311 Computer Graphics (PAM LAB A); 11:00-13:00 SMA2308 Intro. Computational Maths (PAM LAB B) | Afternoon 13:30-15:00 (~1.5h) | Review; write up one exercise solution cleanly for your portfolio | - | 1 | Not Started
50 | 2026-11-07 | Saturday | Phase 3: Specialization Practice | Week 7: Specialization Exercises I | No scheduled classes | Deep-work block (~3h) | Deep work: ARENA-style exercise set, part 2 | - | 3 | Not Started
51 | 2026-11-08 | Sunday | Phase 3: Specialization Practice | Week 7: Specialization Exercises I | No scheduled classes | Deep-work + weekly review (~2.5h) | Weekly review + plan week 8 | - | 2.5 | Not Started
52 | 2026-11-09 | Monday | Phase 3: Specialization Practice | Week 8: Scope Your Portfolio Project | 08:00-10:00 SMA2321 Numerical Analysis I (CLB106) | Evening 18:00-19:30 (~1.5h) | Brainstorm 3 project ideas (1 alignment, 1 verification, 1 hybrid); pick one | - | 1.5 | Not Started
53 | 2026-11-10 | Tuesday | Phase 3: Specialization Practice | Week 8: Scope Your Portfolio Project | 08:00-10:00 STA2300 Theory of Estimation (CLB103); 10:00-12:00 SMA2301 Real Analysis I (CTC201) | Evening 18:00-20:00 (~2h) | Write a 1-page project proposal: goal, method, success criteria | - | 2 | Not Started
54 | 2026-11-11 | Wednesday | Phase 3: Specialization Practice | Week 8: Scope Your Portfolio Project | 10:00-12:00 SMA2303 Group Theory I (CTC202); 16:00-18:00 SMA2322 Fluid Mechanics I (CTC04) | Morning 08:00-09:30 + Evening 18:30-20:00 (~3h) | BlueDot AISF Week 7: 'AI Policy Landscape' (course wrap-up) | aisafetyfundamentals.com | 1.5 | Not Started
55 | 2026-11-12 | Thursday | Phase 3: Specialization Practice | Week 8: Scope Your Portfolio Project | 14:00-15:00 SMA2306 Linear Algebra II (CTC204); 16:00-17:00 SMA2304 ODE I (NSC Lobby) | Morning (free) + Evening 17:30-19:00 (~2h) | Set up project repo structure; write README skeleton | GitHub | 1.5 | Not Started
56 | 2026-11-13 | Friday | Phase 3: Specialization Practice | Week 8: Scope Your Portfolio Project | 09:00-11:00 ICS2311 Computer Graphics (PAM LAB A); 11:00-13:00 SMA2308 Intro. Computational Maths (PAM LAB B) | Afternoon 13:30-15:00 (~1.5h) | Sanity-check your proposal against a real ARENA/MATS project example online | - | 1 | Not Started
57 | 2026-11-14 | Saturday | Phase 3: Specialization Practice | Week 8: Scope Your Portfolio Project | No scheduled classes | Deep-work block (~3h) | Deep work: begin data/model setup for the project | - | 3 | Not Started
58 | 2026-11-15 | Sunday | Phase 3: Specialization Practice | Week 8: Scope Your Portfolio Project | No scheduled classes | Deep-work + weekly review (~2.5h) | Finalize project plan for the next 4 weeks | - | 2.5 | Not Started
59 | 2026-11-16 | Monday | Phase 4: Portfolio Project | Week 9: Portfolio Project - Build Week 1 | 08:00-10:00 SMA2321 Numerical Analysis I (CLB106) | Evening 18:00-19:30 (~1.5h) | Project: data / environment setup | - | 1.5 | Not Started
60 | 2026-11-17 | Tuesday | Phase 4: Portfolio Project | Week 9: Portfolio Project - Build Week 1 | 08:00-10:00 STA2300 Theory of Estimation (CLB103); 10:00-12:00 SMA2301 Real Analysis I (CTC201) | Evening 18:00-20:00 (~2h) | Project: core implementation, part 1 | - | 2 | Not Started
61 | 2026-11-18 | Wednesday | Phase 4: Portfolio Project | Week 9: Portfolio Project - Build Week 1 | 10:00-12:00 SMA2303 Group Theory I (CTC202); 16:00-18:00 SMA2322 Fluid Mechanics I (CTC04) | Morning 08:00-09:30 + Evening 18:30-20:00 (~3h) | Project: core implementation, part 2 | - | 1.5 | Not Started
62 | 2026-11-19 | Thursday | Phase 4: Portfolio Project | Week 9: Portfolio Project - Build Week 1 | 14:00-15:00 SMA2306 Linear Algebra II (CTC204); 16:00-17:00 SMA2304 ODE I (NSC Lobby) | Morning (free) + Evening 17:30-19:00 (~2h) | Project: supporting math/proof work (if verification-focused) | - | 1.5 | Not Started
63 | 2026-11-20 | Friday | Phase 4: Portfolio Project | Week 9: Portfolio Project - Build Week 1 | 09:00-11:00 ICS2311 Computer Graphics (PAM LAB A); 11:00-13:00 SMA2308 Intro. Computational Maths (PAM LAB B) | Afternoon 13:30-15:00 (~1.5h) | Debug + review progress against proposal | - | 1 | Not Started
64 | 2026-11-21 | Saturday | Phase 4: Portfolio Project | Week 9: Portfolio Project - Build Week 1 | No scheduled classes | Deep-work block (~3h) | Deep work: major implementation push | - | 3 | Not Started
65 | 2026-11-22 | Sunday | Phase 4: Portfolio Project | Week 9: Portfolio Project - Build Week 1 | No scheduled classes | Deep-work + weekly review (~2.5h) | Weekly review; log blockers and next steps | - | 2.5 | Not Started
66 | 2026-11-23 | Monday | Phase 4: Portfolio Project | Week 10: Portfolio Project - Build Week 2 | 08:00-10:00 SMA2321 Numerical Analysis I (CLB106) | Evening 18:00-19:30 (~1.5h) | Project: extend core implementation | - | 1.5 | Not Started
67 | 2026-11-24 | Tuesday | Phase 4: Portfolio Project | Week 10: Portfolio Project - Build Week 2 | 08:00-10:00 STA2300 Theory of Estimation (CLB103); 10:00-12:00 SMA2301 Real Analysis I (CTC201) | Evening 18:00-20:00 (~2h) | Project: run first experiments / proof attempts | - | 2 | Not Started
68 | 2026-11-25 | Wednesday | Phase 4: Portfolio Project | Week 10: Portfolio Project - Build Week 2 | 10:00-12:00 SMA2303 Group Theory I (CTC202); 16:00-18:00 SMA2322 Fluid Mechanics I (CTC04) | Morning 08:00-09:30 + Evening 18:30-20:00 (~3h) | Project: analyze first results; adjust approach if needed | - | 1.5 | Not Started
69 | 2026-11-26 | Thursday | Phase 4: Portfolio Project | Week 10: Portfolio Project - Build Week 2 | 14:00-15:00 SMA2306 Linear Algebra II (CTC204); 16:00-17:00 SMA2304 ODE I (NSC Lobby) | Morning (free) + Evening 17:30-19:00 (~2h) | Project: strengthen weakest part of implementation | - | 1.5 | Not Started
70 | 2026-11-27 | Friday | Phase 4: Portfolio Project | Week 10: Portfolio Project - Build Week 2 | 09:00-11:00 ICS2311 Computer Graphics (PAM LAB A); 11:00-13:00 SMA2308 Intro. Computational Maths (PAM LAB B) | Afternoon 13:30-15:00 (~1.5h) | Debug + review progress against proposal | - | 1 | Not Started
71 | 2026-11-28 | Saturday | Phase 4: Portfolio Project | Week 10: Portfolio Project - Build Week 2 | No scheduled classes | Deep-work block (~3h) | Deep work: major implementation push | - | 3 | Not Started
72 | 2026-11-29 | Sunday | Phase 4: Portfolio Project | Week 10: Portfolio Project - Build Week 2 | No scheduled classes | Deep-work + weekly review (~2.5h) | Weekly review; log blockers and next steps | - | 2.5 | Not Started
73 | 2026-11-30 | Monday | Phase 4: Portfolio Project | Week 11: Portfolio Project - Build Week 3 + Draft Writeup | 08:00-10:00 SMA2321 Numerical Analysis I (CLB106) | Evening 18:00-19:30 (~1.5h) | Project: finalize experiments / proofs | - | 1.5 | Not Started
74 | 2026-12-01 | Tuesday | Phase 4: Portfolio Project | Week 11: Portfolio Project - Build Week 3 + Draft Writeup | 08:00-10:00 STA2300 Theory of Estimation (CLB103); 10:00-12:00 SMA2301 Real Analysis I (CTC201) | Evening 18:00-20:00 (~2h) | Project: collect and organize results/evidence | - | 2 | Not Started
75 | 2026-12-02 | Wednesday | Phase 4: Portfolio Project | Week 11: Portfolio Project - Build Week 3 + Draft Writeup | 10:00-12:00 SMA2303 Group Theory I (CTC202); 16:00-18:00 SMA2322 Fluid Mechanics I (CTC04) | Morning 08:00-09:30 + Evening 18:30-20:00 (~3h) | Start writeup: introduction + method section | - | 1.5 | Not Started
76 | 2026-12-03 | Thursday | Phase 4: Portfolio Project | Week 11: Portfolio Project - Build Week 3 + Draft Writeup | 14:00-15:00 SMA2306 Linear Algebra II (CTC204); 16:00-17:00 SMA2304 ODE I (NSC Lobby) | Morning (free) + Evening 17:30-19:00 (~2h) | Writeup: results section | - | 1.5 | Not Started
77 | 2026-12-04 | Friday | Phase 4: Portfolio Project | Week 11: Portfolio Project - Build Week 3 + Draft Writeup | 09:00-11:00 ICS2311 Computer Graphics (PAM LAB A); 11:00-13:00 SMA2308 Intro. Computational Maths (PAM LAB B) | Afternoon 13:30-15:00 (~1.5h) | Writeup: discussion + limitations section | - | 1 | Not Started
78 | 2026-12-05 | Saturday | Phase 4: Portfolio Project | Week 11: Portfolio Project - Build Week 3 + Draft Writeup | No scheduled classes | Deep-work block (~3h) | Deep work: finish first full writeup draft | - | 3 | Not Started
79 | 2026-12-06 | Sunday | Phase 4: Portfolio Project | Week 11: Portfolio Project - Build Week 3 + Draft Writeup | No scheduled classes | Deep-work + weekly review (~2.5h) | Weekly review; list polish items for next week | - | 2.5 | Not Started
80 | 2026-12-07 | Monday | Phase 4: Portfolio Project | Week 12: Polish, Writeup & GitHub Finalization | 08:00-10:00 SMA2321 Numerical Analysis I (CLB106) | Evening 18:00-19:30 (~1.5h) | Revise writeup for clarity based on your own re-read | - | 1.5 | Not Started
81 | 2026-12-08 | Tuesday | Phase 4: Portfolio Project | Week 12: Polish, Writeup & GitHub Finalization | 08:00-10:00 STA2300 Theory of Estimation (CLB103); 10:00-12:00 SMA2301 Real Analysis I (CTC201) | Evening 18:00-20:00 (~2h) | Clean up code: comments, structure, remove dead code | - | 2 | Not Started
82 | 2026-12-09 | Wednesday | Phase 4: Portfolio Project | Week 12: Polish, Writeup & GitHub Finalization | 10:00-12:00 SMA2303 Group Theory I (CTC202); 16:00-18:00 SMA2322 Fluid Mechanics I (CTC04) | Morning 08:00-09:30 + Evening 18:30-20:00 (~3h) | Write a clear top-level README with results and how to reproduce | - | 1.5 | Not Started
83 | 2026-12-10 | Thursday | Phase 4: Portfolio Project | Week 12: Polish, Writeup & GitHub Finalization | 14:00-15:00 SMA2306 Linear Algebra II (CTC204); 16:00-17:00 SMA2304 ODE I (NSC Lobby) | Morning (free) + Evening 17:30-19:00 (~2h) | Add visuals/plots if useful; finalize repo structure | - | 1.5 | Not Started
84 | 2026-12-11 | Friday | Phase 4: Portfolio Project | Week 12: Polish, Writeup & GitHub Finalization | 09:00-11:00 ICS2311 Computer Graphics (PAM LAB A); 11:00-13:00 SMA2308 Intro. Computational Maths (PAM LAB B) | Afternoon 13:30-15:00 (~1.5h) | Proofread everything; publish repo as public | - | 1 | Not Started
85 | 2026-12-12 | Saturday | Phase 4: Portfolio Project | Week 12: Polish, Writeup & GitHub Finalization | No scheduled classes | Deep-work block (~3h) | Deep work: optional short blog-style post summarizing the project | - | 3 | Not Started
86 | 2026-12-13 | Sunday | Phase 4: Portfolio Project | Week 12: Polish, Writeup & GitHub Finalization | No scheduled classes | Deep-work + weekly review (~2.5h) | Weekly review: project complete - celebrate the milestone | - | 2.5 | Not Started
87 | 2026-12-14 | Monday | Phase 5: Apply & Wrap-Up | Week 13: Applications Week | 08:00-10:00 SMA2321 Numerical Analysis I (CLB106) | Evening 18:00-19:30 (~1.5h) | Update CV/resume with new skills + project | - | 1.5 | Not Started
88 | 2026-12-15 | Tuesday | Phase 5: Apply & Wrap-Up | Week 13: Applications Week | 08:00-10:00 STA2300 Theory of Estimation (CLB103); 10:00-12:00 SMA2301 Real Analysis I (CTC201) | Evening 18:00-20:00 (~2h) | Update LinkedIn/portfolio site with project + learning journey | - | 2 | Not Started
89 | 2026-12-16 | Wednesday | Phase 5: Apply & Wrap-Up | Week 13: Applications Week | 10:00-12:00 SMA2303 Group Theory I (CTC202); 16:00-18:00 SMA2322 Fluid Mechanics I (CTC04) | Morning 08:00-09:30 + Evening 18:30-20:00 (~3h) | Check next ARENA cohort dates; prepare application materials | bluedot.org/courses/arena | 1.5 | Not Started
90 | 2026-12-17 | Thursday | Phase 5: Apply & Wrap-Up | Week 13: Applications Week | 14:00-15:00 SMA2306 Linear Algebra II (CTC204); 16:00-17:00 SMA2304 ODE I (NSC Lobby) | Morning (free) + Evening 17:30-19:00 (~2h) | Research MATS + Anthropic Fellows application windows and requirements | matsprogram.org | 1.5 | Not Started
91 | 2026-12-18 | Friday | Phase 5: Apply & Wrap-Up | Week 13: Applications Week | 09:00-11:00 ICS2311 Computer Graphics (PAM LAB A); 11:00-13:00 SMA2308 Intro. Computational Maths (PAM LAB B) | Afternoon 13:30-15:00 (~1.5h) | Shortlist 3-5 RA/PhD/scholarship listings matching Path 1 or 2; note deadlines | jobs.ac.uk / university sites | 1 | Not Started
92 | 2026-12-19 | Saturday | Phase 5: Apply & Wrap-Up | Week 13: Applications Week | No scheduled classes | Deep-work block (~3h) | Deep work: submit 1-2 applications or draft outreach emails | - | 3 | Not Started
93 | 2026-12-20 | Sunday | Phase 5: Apply & Wrap-Up | Week 13: Applications Week | No scheduled classes | Deep-work + weekly review (~2.5h) | Weekly review; plan applications still pending | - | 2.5 | Not Started
94 | 2026-12-21 | Monday | Phase 5: Apply & Wrap-Up | Week 14: Buffer, Review & Next-Cycle Planning | 08:00-10:00 SMA2321 Numerical Analysis I (CLB106) | Evening 18:00-19:30 (~1.5h) | Buffer: catch up on any missed task from the last 13 weeks | - | 1.5 | Not Started
95 | 2026-12-22 | Tuesday | Phase 5: Apply & Wrap-Up | Week 14: Buffer, Review & Next-Cycle Planning | 08:00-10:00 STA2300 Theory of Estimation (CLB103); 10:00-12:00 SMA2301 Real Analysis I (CTC201) | Evening 18:00-20:00 (~2h) | Buffer: catch up / revisit your weakest topic | - | 2 | Not Started
96 | 2026-12-23 | Wednesday | Phase 5: Apply & Wrap-Up | Week 14: Buffer, Review & Next-Cycle Planning | 10:00-12:00 SMA2303 Group Theory I (CTC202); 16:00-18:00 SMA2322 Fluid Mechanics I (CTC04) | Morning 08:00-09:30 + Evening 18:30-20:00 (~3h) | Revisit the topic you found hardest; redo one exercise | - | 1.5 | Not Started
97 | 2026-12-24 | Thursday | Phase 5: Apply & Wrap-Up | Week 14: Buffer, Review & Next-Cycle Planning | 14:00-15:00 SMA2306 Linear Algebra II (CTC204); 16:00-17:00 SMA2304 ODE I (NSC Lobby) | Morning (free) + Evening 17:30-19:00 (~2h) | Revisit second-hardest topic; redo one exercise | - | 1.5 | Not Started
98 | 2026-12-25 | Friday | Phase 5: Apply & Wrap-Up | Week 14: Buffer, Review & Next-Cycle Planning | 09:00-11:00 ICS2311 Computer Graphics (PAM LAB A); 11:00-13:00 SMA2308 Intro. Computational Maths (PAM LAB B) | Afternoon 13:30-15:00 (~1.5h) | Tidy all notes/repos into one clear index document | - | 1 | Not Started
99 | 2026-12-26 | Saturday | Phase 5: Apply & Wrap-Up | Week 14: Final review | No scheduled classes | Deep-work block (~3h) | Review all 100 days: what got Done vs Skipped; write 5 honest lessons learned | Your own tracker + notes | 3 | Not Started
100 | 2026-12-27 | Sunday | Phase 5: Apply & Wrap-Up | Week 14: Goal-setting for Jan/Feb | No scheduled classes | Deep-work + weekly review (~2.5h) | Set 3 concrete goals for Jan/Feb (e.g. apply to next ARENA cohort, finish a second project); plan your next 100-day cycle | - | 2.5 | Not Started

## Progress Dashboard
100-Day Tracker - Progress Dashboard
Total days in plan | 100
Days marked Done | 0
Days marked In Progress | 0
Days marked Skipped | 0
Days Not Started | 100
% Complete (Done / Total) | 0%
Target for 2/3 completion (days) | 67
Days still needed to hit 2/3 target | 67
Progress by Phase
Phase | Total Days | Days Done | % Complete
Phase 1: Foundations | 16 | 0 | 0%
Phase 2: Deep Learning & Alignment Core | 28 | 0 | 0%
Phase 3: Specialization Practice | 14 | 0 | 0%
Phase 4: Portfolio Project | 28 | 0 | 0%
Phase 5: Apply & Wrap-Up | 14 | 0 | 0%
Tip: update the Status column in the '100-Day Tracker' sheet daily. This dashboard updates automatically.

## Key Resources
Key Resources & Platforms
Resource | Link | Used for
BlueDot Impact - AI Safety Fundamentals | https://aisafetyfundamentals.com | Core AI safety/alignment curriculum (Path 1)
ARENA (Alignment Research Engineer Accelerator) | https://bluedot.org/courses/arena | Applied ML-for-safety bootcamp (Path 1, apply once ready)
MATS (ML Alignment Theory Scholars) | https://www.matsprogram.org | Research mentorship (Path 1, apply after ARENA/foundations)
fast.ai - Practical Deep Learning | https://course.fast.ai | Deep learning foundations
PyTorch Tutorials | https://pytorch.org/tutorials | Core ML framework fluency
3Blue1Brown - Essence of Linear Algebra | https://www.3blue1brown.com/topics/linear-algebra | Math refresh
MIT OCW 18.05 (Probability) | https://ocw.mit.edu | Math refresh
Theorem Proving in Lean 4 | https://leanprover.github.io/theorem_proving_in_lean4/ | Formal verification foundations (Path 2)
Mathematics in Lean | https://leanprover-community.github.io/mathematics_in_lean/ | Formal verification foundations (Path 2)
Marabou | https://github.com/NeuralNetworkVerification/Marabou | Neural network verification tool (Path 2)
alpha-beta-CROWN | https://github.com/Verified-Intelligence/alpha-beta-CROWN | Neural network verification tool (Path 2)
Neel Nanda - Mechanistic Interpretability | https://www.neelnanda.io | Interpretability intro (Path 1)
TransformerLens | https://github.com/TransformerLensOrg/TransformerLens | Mechanistic interpretability tooling (Path 1)
The Illustrated Transformer (Jay Alammar) | https://jalammar.github.io | Transformer intuition